## Lien Waiver Tracker
Construction Lien Waiver Collection Tracker
Track conditional and unconditional lien waivers (progress and final) by party, draw and payment — so no payment is released without the matching waiver. Days Outstanding, Payment Hold Flag and Status update automatically. SAMPLE rows are examples. Need automatic Email, SMS and WhatsApp reminders? Try Remindax → https://www.remindax.com/ ¦ Track-and-remind only; not legal advice; lien-waiver forms and rules vary by state — confirm with counsel and the statutory forms that apply.
Sample Flag | Project (sample) | Draw / Pay App # | Party (sample) | Party Type | Waiver Type | Through Date | Payment Amount (sample) | Payment Scheduled Date | Waiver Requested Date | Waiver Received Date | Payment Released Date | Reminder Status | Owner | Days Outstanding | Payment Hold Flag | Status | Queue Key (helper)
SAMPLE | Riverside Medical Office (sample) | Draw 2 | Apex Electric (sample) | Subcontractor | Conditional Progress | 2026-08-31 | 48500 | 2026-10-28 | 2026-10-03 |  |  | Requested | PM — D. Alvarez (sample)
SAMPLE | Riverside Medical Office (sample) | Draw 2 | Summit Concrete Supply (sample) | Supplier | Conditional Progress | 2026-08-31 | 22100 | 2026-10-13 | 2026-10-05 |  |  | Reminder Sent | Project Accountant — J. Kim (sample)
SAMPLE | Oak Street Apartments (sample) | Draw 3 | Delta Plumbing (sample) | Subcontractor | Conditional Progress | 2026-09-07 | 31750 | 2026-11-07 | 2026-09-18 |  |  | Reminder Sent | Project Accountant — J. Kim (sample)
SAMPLE | Oak Street Apartments (sample) | Draw 3 | Ironworks Steel (sample) | Subcontractor | Unconditional Progress | 2026-08-07 | 64000 | 2026-10-07 | 2026-10-02 |  |  | Requested | AP — S. Moore (sample)
SAMPLE | Northgate Warehouse (sample) | Draw 1 | BlueLine Roofing (sample) | Subcontractor | Conditional Progress | 2026-08-24 | 18900 | 2026-09-28 | 2026-09-13 |  | 2026-09-30 | Reminder Sent | AP — S. Moore (sample)
SAMPLE | Northgate Warehouse (sample) | Draw 1 | Granite Masonry (sample) | Sub-tier | Unconditional Progress | 2026-08-24 | 9400 | 2026-10-03 | 2026-09-23 | 2026-09-28 | 2026-10-04 | Not Started | Superintendent — T. Lane (sample)
SAMPLE | Elm School Renovation (sample) | Draw 5 | Metro HVAC (sample) | Subcontractor | Unconditional Final | 2026-09-18 | 87500 | 2026-10-01 | 2026-09-08 | 2026-10-06 | 2026-10-02 | Not Started | PM — D. Alvarez (sample)
SAMPLE | Elm School Renovation (sample) | Draw 4 | Coastal Glazing (sample) | Subcontractor | Conditional Final | 2026-09-23 | 41200 | 2026-10-20 |  |  |  | Not Started | Superintendent — T. Lane (sample)
SAMPLE | Riverside Medical Office (sample) | Draw 1 | Apex Electric (sample) | Subcontractor | Unconditional Progress | 2026-08-01 | 51200 | 2026-09-08 | 2026-08-29 | 2026-09-05 | 2026-09-08 | Complete | PM — D. Alvarez (sample)
SAMPLE | Oak Street Apartments (sample) | Draw 3 | Valley Lumber (sample) | Supplier | Conditional Progress | 2026-09-07 | 12650 |  | 2026-10-06 |  |  | Requested | Project Accountant — J. Kim (sample)
Formulas:
Days Outstanding = IF(OR([Waiver Requested Date]="",[Waiver Received Date]<>"",[Reminder Status]="Complete"),"",TODAY()-[Waiver Requested Date])

## Dashboard
Lien Waiver Collection Dashboard
Auto-calculated from Lien Waiver Tracker. Counts only real rows (blank rows stay blank). Track-and-remind only; not legal advice; lien-waiver forms and rules vary by state — confirm with counsel and the statutory forms that apply.
Collection Overview
Total Waivers Tracked
Released Without Waiver
Overdue
Due Soon
Requested / Pending
Received / Complete
Missing Date
Payment Holds (HOLD — No Waiver)
Payments Released Without Waiver (flag)
Collection Health Score % (received ÷ total)
Missing-Waiver Queue — top 10 open by days outstanding (ties broken by row, no duplicates)
Party | Project | Draw | Waiver Type | Days Outstanding | Hold Flag
Completion % by Project
Project | Waivers | Received | Completion %
Completion % by Draw / Pay App
Draw | Waivers | Received | Completion %
By Party Type
Subcontractor
Supplier
Sub-tier
GC
Need automatic Email, SMS and WhatsApp reminders to chase every lien waiver before the draw? Try Remindax
https://www.remindax.com/

## Instructions
How to use this Construction Lien Waiver Collection Tracker
Track-and-remind only; not legal advice; lien-waiver forms and rules vary by state — confirm with counsel and the statutory forms that apply.
1. How to use
Replace SAMPLE rows on Lien Waiver Tracker. One row per waiver expected — per party, per draw / pay application, per waiver type. Enter the Payment Scheduled Date and Waiver Requested Date when you ask for the waiver, the Waiver Received Date when it arrives, and the Payment Released Date when the payment goes out. Days Outstanding, Payment Hold Flag and Status are calculated.
2. Conditional vs unconditional (neutral overview)
In general terms, a conditional waiver is commonly written to take effect only once the stated payment is actually received, while an unconditional waiver is commonly written to take effect on signing. Progress waivers cover a payment through a stated date; final waivers cover the final payment. Exact wording, effect and required forms vary by state — this sheet only records which type you requested and received.
3. Payment hold logic
Released Without Waiver (dark red) — a Payment Released Date exists and the waiver is not received, or was received after the release. HOLD — No Waiver (orange) — a payment is scheduled and the waiver is not received yet. Clear — otherwise.
4. Status meanings (in order)
Blank row → blank. Missing Date — no Waiver Requested Date. Received / Complete — Waiver Received Date filled or Reminder Status Complete. Released Without Waiver — payment released, waiver not received. Overdue — outstanding more than 14 days, or the payment date has arrived without the waiver. Due Soon — payment scheduled within 7 days. Requested / Pending — otherwise.
5. Dashboard
The Missing-Waiver Queue ranks open waivers by days outstanding using the Queue Key helper (Days Outstanding + ROW/10000), so ties never show the same row twice. Completion % per project and per draw = received ÷ total waivers. Edit the project and draw lists on Lookup to match your jobs.
Need automatic Email, SMS and WhatsApp reminders to chase every lien waiver before the draw? Try Remindax
https://www.remindax.com/

## Lookup
Project (sample) | Draw / Pay App # | Party Type | Waiver Type | Reminder Status | Sample Flag | Status Labels | Hold Flags | Owner (sample)
Riverside Medical Office (sample) | Draw 1 | Subcontractor | Conditional Progress | Not Started | SAMPLE | Requested / Pending | Clear | PM — D. Alvarez (sample)
Oak Street Apartments (sample) | Draw 2 | Supplier | Unconditional Progress | Requested |  | Due Soon | HOLD — No Waiver | Project Accountant — J. Kim (sample)
Northgate Warehouse (sample) | Draw 3 | Sub-tier | Conditional Final | Reminder Sent |  | Overdue | Released Without Waiver | AP — S. Moore (sample)
Elm School Renovation (sample) | Draw 4 | GC | Unconditional Final | Complete |  | Released Without Waiver |  | Superintendent — T. Lane (sample)
| Draw 5 |  |  |  |  | Received / Complete
| Final |  |  |  |  | Missing Date
Notes
Days Outstanding = TODAY − Waiver Requested Date while the waiver is not received (blank once received or Complete). Payment Hold Flag: Released Without Waiver when a Payment Released Date exists and the waiver is not received or was received after release; HOLD — No Waiver when a payment is scheduled and the waiver is not received; else Clear. Status order: blank row → blank; Missing Date (no requested date) → Received / Complete → Released Without Waiver → Overdue (outstanding > 14 days or payment date reached) → Due Soon (payment within 7 days) → Requested / Pending. Queue Key = Days Outstanding + ROW()/10000 so the Dashboard queue never repeats a row on ties. Track-and-remind only; not legal advice; lien-waiver forms and rules vary by state — confirm with counsel and the statutory forms that apply. SAMPLE rows are examples.