## TCO Tracker
Temporary Certificate of Occupancy Tracker
Track each TCO expiration, open punch-list conditions, extension requests, and change-of-use review dates by property. SAMPLE rows are examples. Need automatic Email, SMS and WhatsApp reminders? Try Remindax → https://www.remindax.com/ ¦ Date/status only — does not issue a TCO or determine legal occupancy.
Sample Flag | Property / Site (sample) | Permit / TCO Ref (sample) | Issuing Authority (sample) | TCO Issue Date | TCO Expiration | Open Conditions / Punch-List Items (count) | Extension Requested (Yes/No) | Extension Request Date | Change-of-Use Review Due | Reminder Status | Owner | Days Left (TCO) | Days to Change-of-Use Review | Status
SAMPLE | 100 Market Tower (sample) | TCO-2026-014 (sample) | City Building Dept (sample) | 2026-08-06 | 2026-10-30 | 3 | Yes | 2026-09-30 | 2027-02-02 | Reminder Sent | Facilities — L. Ortiz (sample)
SAMPLE | Riverfront Plaza — Suite 200 (sample) | TCO-2026-021 (sample) | City Building Dept (sample) | 2026-07-07 | 2026-09-27 | 1 | No |  | 2027-04-23 | Not Started | GC PM — K. Lee (sample)
SAMPLE | East Wing Addition (sample) | TCO-2025-088 (sample) | County Fire Marshal (sample) | 2026-06-07 | 2026-11-19 | 0 | No |  | 2026-11-14 | Scheduled | Owner Rep — M. Diaz (sample)
SAMPLE | Warehouse B Fit-Out (sample) | TCO-2026-003 (sample) | State Occupancy Board (sample) | 2026-09-05 | 2026-12-24 | 4 | No |  | 2027-04-03 | Not Started | Facilities — L. Ortiz (sample)
SAMPLE | Clinic Renovation Phase 2 (sample) | TCO-2026-030 (sample) | City Building Dept (sample) | 2026-09-15 | 2027-04-23 | 0 | No |  | 2027-06-12 | Complete | Property Mgmt (sample)
SAMPLE | 100 Market Tower (sample) | TCO-2026-041 (sample) | County Fire Marshal (sample) | 2026-09-25 |  | 2 | Yes | 2026-10-05 | 2027-01-03 | Reminder Sent | GC PM — K. Lee (sample)
SAMPLE | Riverfront Plaza — Suite 200 (sample) | TCO-2026-055 (sample) | City Building Dept (sample) | 2026-08-21 | 2027-03-04 | 0 | No |  | 2027-08-01 | Not Started | Owner Rep — M. Diaz (sample)
SAMPLE | East Wing Addition (sample) | TCO-2026-062 (sample) | Other Authority | 2026-07-27 | 2026-10-23 | 0 | Yes | 2026-10-03 | 2026-12-04 | Scheduled | Facilities — L. Ortiz (sample)
Formulas:
Days Left (TCO) = IF([TCO Expiration]="","",[TCO Expiration]-TODAY())
Days to Change-of-Use Review = IF([Change-of-Use Review Due]="","",[Change-of-Use Review Due]-TODAY())

## Dashboard
Temporary Certificate of Occupancy Dashboard
Auto-calculated from TCO Tracker (SAMPLE rows are examples). Hard occupancy deadlines, open conditions, and extension requests. Date/status only — does not issue a TCO.
Portfolio Overview
Total TCOs Tracked
Expired
Extension Pending
Due Soon
OK
Complete
Missing Date
Open Conditions (sum)
Action Needed (expired + pending + due soon + missing)
On-time Score %
Need automatic Email, SMS and WhatsApp reminders before a TCO expires? Try Remindax
https://www.remindax.com/

## Instructions
How to use this Temporary Certificate of Occupancy Tracker
1. Getting started
Replace SAMPLE rows on the TCO Tracker sheet with your properties. One row per temporary certificate. Use dropdowns for Extension Requested, Reminder Status, Site, Authority, and Owner. Enter TCO Expiration — Days Left and Status calculate automatically.
2. Column guide
TCO Expiration drives Days Left (TCO). Open Conditions is a count of punch-list items still open. Extension Requested = Yes/No; when Yes and Days Left ≤ 30, Status becomes Extension Pending. Change-of-Use Review Due is optional and has its own Days to Change-of-Use Review column.
3. Status meanings
Missing Date — TCO Expiration blank. Complete — Reminder Status is Complete. Expired — Days Left < 0. Extension Pending — Extension Requested is Yes and Days Left ≤ 30. Due Soon — Days Left ≤ 60, OR open conditions > 0 and Days Left ≤ 90. OK — otherwise.
4. Due Soon threshold
Primary Due Soon window is 60 days. Rows with open punch-list items also enter Due Soon when 90 or fewer days remain on the TCO.
5. Data privacy
Date and status only. Do not store unnecessary personal data. This workbook does not issue a TCO, approve occupancy, or make legal determinations about change of use.
Need automatic Email, SMS and WhatsApp reminders before a temporary certificate expires? Try Remindax
https://www.remindax.com/

## Lookup
Extension Requested | Reminder Status | Sample Flag | Status Labels | Property / Site (sample) | Issuing Authority (sample) | Owner (sample)
Yes | Not Started | SAMPLE | OK | 100 Market Tower (sample) | City Building Dept (sample) | Facilities — L. Ortiz (sample)
No | Reminder Sent |  | Due Soon | Riverfront Plaza — Suite 200 (sample) | County Fire Marshal (sample) | GC PM — K. Lee (sample)
| Scheduled |  | Extension Pending | East Wing Addition (sample) | State Occupancy Board (sample) | Owner Rep — M. Diaz (sample)
| Complete |  | Expired | Warehouse B Fit-Out (sample) | Other Authority | Property Mgmt (sample)
|  |  | Complete | Clinic Renovation Phase 2 (sample)
|  |  | Missing Date | Other site
Notes
Status order: Missing Date if TCO Expiration is blank; Complete if Reminder Status is Complete; Expired if Days Left (TCO) < 0; Extension Pending if Extension Requested is Yes and Days Left ≤ 30; Due Soon if Days Left ≤ 60 OR (open punch-list items > 0 AND Days Left ≤ 90); else OK. Date and status only — does not issue a TCO or determine legal occupancy. SAMPLE rows are examples.